## Revisions
Version | Date Modified | Description of Modified Items | Associated requirements
1 | 2021-04-12 | Deleting Particle Flux Monitor from Composition Determination (05.03.03) after Concept Baseline Review, and revising Payload section | N/A
2 | 2021-04-14 | Structures, and payload changes (Support Bus --> SC; APIC moved to payload section; Star trackers moved to ADCS) | N/A
3 | 2021-04-16 | Adding more detail to Data Harness section for C&DH and work packages for vehicle structure development; additional testing included for flight system integration | N/A
4 | 2021-04-28 | Updates to System I&T products (moving the FS facilities); added numbering scheme; added SunTrackers to GNC | N/A
5 | 2021-05-14 | Payload terminology changed to IHM | N/A
6 | 2021-05-20 | Addition of Mission Analysis/Orbits as part of Mission Development (changed from SciTech) | N/A

## WBS revision version
Key |  |  |  |  | COSMIC Project Work Breakdown Structure
Product Element
Organizational Element
Contracted Element
Work Package
Contractor Work Package
Statement of Work
Level 1 |  | Level 2 | Level 3 | Level 4 Code | Level 4 | Level 5 Code | Level 5 | Level 6 Code | Level 6 | Level 7 Code | Level 7
C.O.S.M.I.C Project |  | Program Project Management 01 | Business Management 01.01 | 01.01.01 | Schedule Management | 01.01.01.01 | Develop Programmatic Schedule
|  |  |  | 01.01.02 | Resource Management | 01.01.02.01 | Organize Resources
[6 empty] | 01.01.02.02 | Allocate Resources
|  |  |  | 01.01.03 | Cost Management | 01.01.03.01 | Develop Programmatic Budget
|  |  | Project Management 01.02 | 01.02.01 | WBS Management | 01.02.01.01 | Develop WBS
|  |  |  | 01.02.02 | Performance Management | 01.02.01.02 | Monitor and Evaluate Project Performance
|  |  | Procurement Management 01.03 | 01.03.01 | Plan Procurements
|  |  |  | 01.03.02 | Administer Procurements
|  |  |  | 01.03.03 | Close Procurements
|  |  | Program Risk Management 01.04 | 01.04.01 | Procure Programmatic Risk
|  | Program Systems Engineering 02 | Systems Engineering Management 02.01 | 02.01.01 | Manage all systems engineers and governing documents
|  |  |  | 02.01.02 | Schedule Meetings and Deliverable Dates
|  |  | Concepts of Operations Management 02.02 | 02.02.01 | Define Alternative Design Solutions
|  |  |  | 02.02.02 | Create Alternative Design Concepts
|  |  |  | 02.02.03 | Analyze Each Alternative Design Solution
|  |  |  | 02.02.04 | Select the Best Design Solution Alternative
|  |  |  | 02.02.05 | Increase the Resolution of the Design
|  |  |  | 02.02.06 | Fully Describe the Design Solution
|  |  |  | 02.02.07 | Verify the Design Solution
|  |  |  | 02.02.08 | Validate the Design Solution
|  |  |  | 02.02.09 | Identify Enabling Products
|  |  |  | 02.02.10 | Baseline the Design Solution
|  |  | Requirement Management 02.03 | 02.03.01 | Develop Requirement Breakdown Structure
|  |  |  | 02.03.02 | Receive Requirements and Maintain RBS
|  |  |  | 02.03.03 | Conduct Expectations and Requirement Traceability
|  |  |  | 02.03.04 | Manage Requirement Changes
|  |  | Product Verification and Validation 02.04 | 02.04.01 | Prepare Product Verification and Validation Procedures
|  |  |  | 02.04.02 | Preform Product Verification
|  |  |  | 02.04.03 | Analyze Product Verification Results
|  |  |  | 02.04.04 | Perform Product Validation
|  |  |  | 02.04.05 | Analyze Product Validation Results
|  |  |  | 02.04.06 | Prepare Product Verification/Validation Report
|  |  | Interface Management 02.05 | 02.05.01 | Prepare Interface Management Procedures
|  |  |  | 02.05.02 | Conduct Interface Management during System Design and Product Integration
|  |  |  | 02.05.03 | Conduct Interface Control
|  |  |  | 02.05.04 | Capture Work Products
|  |  | Technical Risk Management 02.06 | 02.06.01 | Prepare Strategy to Conduct Technical Risks Management
|  |  |  | 02.06.02 | Identify Technical Risks
|  |  |  | 02.06.03 | Conduct Technical Risks Assessment
|  |  |  | 02.06.04 | Implement Technical Risk Mitigation
|  |  | Configuration Management 02.07 | 02.07.01 | Conduct traceability between RBS and PBS/WBS
|  |  |  | 02.07.02 | Identify Design Baseline
|  |  |  | 02.07.03 | Manage Design Decision Changes
|  |  |  | 02.07.04 | Maintain the Status of the Configuration Documents (PBS, Changelog, etc..)
|  |  |  | 02.07.05 | Conduct Configuration Audits
|  |  | Technical Data Management 02.08 | 02.08.01 | Prepare for Technical Data Management
|  |  |  | 02.08.02 | Collect and Store Data
|  |  |  | 02.08.03 | Provide Data to Authorized Parties
|  |  | Decision Analysis/ Trade Studies 02.09 | 02.09.01 | Define Criteria for Evaluating Alternative Solutions
|  |  |  | 02.09.02 | Identify Alternative Solutions to Address Decision Issues
|  |  |  | 02.09.03 | Select Evaluation Methods and Tools
|  |  |  | 02.09.04 | Evaluated Alternative Solutions with established criteria
|  |  |  | 02.09.05 | Select Recommended Solutions
|  | Safety and Mission Assurance 03 | Safety and Mission Assurance Management 03.01 | 3.01.01 | Assure that delivered spacecraft and mission segments function for their intended lifetimes
|  |  |  | 3.01.02 | Assure that delivered spacecraft, ground systems, mission operations, and payload meet performance requirements
|  |  | System Safety 03.02 | 03.02.01 | Interface with System Reliability and Technology Readiness
|  |  | System Reliability 03.03 | 03.03.01 | Manage determination systems reliability and risk analysis
|  |  | Technology Readiness 03.04 | 03.04.01 | Ensure that the technology and design documented meets industry standards
|  |  | Quality Assurance 03.05 | 03.05.01 | Verify manufacturing/testing comply with industry standards
|  | Concept Development 04 | Science and Technology (SciTech) 04.01 | 04.01.01 | SciTech Management | 04.01.01.01 | Interface between Flight System Management and payload
|  |  |  | 04.01.02 | SciTech Systems Engineering | 04.01.02.01 | Facilitate communication and interface with Science Development interteams
|  |  |  | 04.01.03 | Science Development | 04.01.03.01 | Advocate for science and innovative technology usage within the scope of the mission
|  |  | Mission Analysis/Orbits 04.02 | 04.02.01 | Mission Analysis/Orbits Management | 04.02.01.01 | Interface between Program Management and Mission Analysis Team
[6 empty] | 04.02.01.02 | Manage Mission Analysis Team Members and Task Allocations
|  |  |  | 04.02.02 | Mission Analysis/Orbits Systems Engineering | 04.02.02.01 | Interface between Mission Analysis Team and other Systems Engineers and Design Teams
|  |  |  | 04.02.03 | Orbital Development | 04.02.03.01 | Develop orbit concepts for mission operation
[6 empty] | 04.02.03.02 | Model orbits and trajectories to test concepts and inform design decisions
[6 empty] | 04.02.03.03 | Develop Emplacement and Stationkeeping approaches
|  |  |  | 04.02.04 | Propulsion and Mass Modeling | 04.02.04.01 | Develop continuous/non-impulsive propulsion modeling tools
[6 empty] | 04.02.04.02 | Develop propulsion mass modeling tools to interface between burn needs and propulsion design
[6 empty] | 04.02.04.03 | Optimize orbital concepts and models in light of propulsion and spacecraft mass requirements
|  | Flight System 05 | Flight System Management 05.01 | 05.01.01 | Interface between Program Project Management, Flight System Management, Safety and Mission Assurance, and Flight System subsystems
|  |  | Flight System Systems Engineering 05.02 | 05.02.01 | Facilitate between Flight System Management and interface with Program Systems Engineering as well as mission risk analysis
|  |  | Propulsion Subsystem 05.03 | 05.03.01 | Propulsion Management | 05.03.01.01 | Interface between other subsystems
[6 empty] | 05.03.01.02 | Communicate with Flight System Management
|  |  |  | 05.03.02 | Primary Chemical Propulsion System (Translation Control) | 05.03.02.01 | Research Optimal Chemical Propulsion System Properties
[6 empty] | 05.03.02.02 | Design Compatible Chemical Propulsion System
[6 empty] | 05.03.02.03 | Run FEA on Chemical Propulsion System
[6 empty] | 05.03.02.04 | Run Thermal Analysis on Chemical Propulsion System
[6 empty] | 05.03.02.05 | Run Burn Analysis on Chemical Propulsion System
[6 empty] | 05.03.02.06 | Manufacture Chemical Propulsion System
[6 empty] | 05.03.02.07 | Test Primary Chemical Propulsion System
|  |  |  | 05.03.03 | Secondary Chemical Propulsion System (Station Keeping and CMG Desaturation) | 05.03.03.01 | Research Optimal Chemical Propulsion System Properties
[6 empty] | 05.03.03.02 | Design Compatible Chemical Propulsion System
[6 empty] | 05.03.03.03 | Run FEA on Chemical Propulsion System
[6 empty] | 05.03.03.04 | Run Thermal Analysis on Chemical Propulsion System
[6 empty] | 05.03.03.05 | Run Burn Analysis on Chemical Propulsion System
[6 empty] | 05.03.03.06 | Manufacture Chemical Propulsion System
[6 empty] | 05.03.03.07 | Test Primary Chemical Propulsion System
|  |  |  | 05.03.04 | Propulsion Functional Testing | 05.03.04.01 | Develop Test Procedures
[6 empty] | 05.03.04.02 | Prepare flight system for Test
[6 empty] | 05.03.04.03 | Perform Propulsion Functional Test to Qualification Standards
[6 empty] | 05.03.04.04 | Produce Testing Report
|  |  |  | 05.03.05 | Propulsion Environmental Testing | 05.03.05.01 | Develop Test Procedures
[6 empty] | 05.03.05.02 | Prepare Support Bus for Test
[6 empty] | 05.03.05.03 | Perform Propulsion Environmental Test to Qualification Standards
[6 empty] | 05.03.05.04 | Produce Testing Report
|  |  | Power Subsystem 05.04 | 05.04.01 | Power Management | 05.04.01.01 | Manage Power Team Members
[6 empty] | 05.04.01.02 | Interface between other subsystems
[6 empty] | 05.04.01.03 | Communicate with Flight System Management
|  |  |  | 05.04.02 | Solar Arrays (ROSAs) | 05.04.02.01 | Investigate Commercially Available ROSA panels
[6 empty] | 05.04.02.02 | Design ROSA Array Sizing
[6 empty] | 05.04.02.03 | Procure Selected ROSA panels
[6 empty] | 05.04.02.04 | Test ROSA Panels
|  |  |  | 05.04.03 | Battery | 05.04.03.01 | Investigate Commercially Available Battery
[6 empty] | 05.04.03.02 | Design Battery Sizing and Configuration
[6 empty] | 05.04.03.03 | Procure Selected Battery
[6 empty] | 05.04.03.04 | Test Battery Configuration
|  |  |  | 05.04.04 | Power Distribution Unit | 05.04.04.01 | Investigate Commercially Power Distribution Units
[6 empty] | 05.04.04.02 | Design Power Distribution Layout and Harness
[6 empty] | 05.04.04.03 | Procure Selected Power Distribution Unit
[6 empty] | 05.04.04.04 | Test Power Distribution Unit
|  |  |  | 05.04.05 | Power Functional Testing | 05.04.05.01 | Develop Test Procedures
[6 empty] | 05.04.05.02 | Prepare Support Bus for Test
[6 empty] | 05.04.05.03 | Perform Power System Functional Test to Qualification Standards
[6 empty] | 05.04.05.04 | Produce Testing Report
|  |  |  | 05.04.06 | Power Environmental Testing | 05.04.06.01 | Develop Test Procedures
[6 empty] | 05.04.06.02 | Prepare Support Bus for Test
[6 empty] | 05.04.06.03 | Perform Power System Environmental Test to Qualification Standards
[6 empty] | 05.04.06.04 | Produce Testing Report
|  |  | Communication Subsystem 05.05 | 05.05.01 | Communication Management | 05.05.01.01 | Manage Communication Team Members
[6 empty] | 05.05.01.02 | Interface between other subsystems
[6 empty] | 05.05.01.03 | Communicate with Flight System Management
|  |  |  | 05.05.02 | X-Band Traveling Wave Tube Amplifier | 05.05.02.01 | Investigate Commercially Available X-Band Components
[6 empty] | 05.05.02.02 | Design and Close X-Band link Budget
[6 empty] | 05.05.02.03 | Procure Selected X-Band Components
[6 empty] | 05.05.02.04 | Test X-Band Components
|  |  |  | 05.05.03 | Ka-Band Traveling Wave Tube Amplifier | 05.05.03.01 | Investigate Commercially Available Ka-Band Components
[6 empty] | 05.05.03.02 | Design and Close Ka-Band link Budget
[6 empty] | 05.05.03.03 | Procure Selected Ka-Band Components
[6 empty] | 05.05.03.04 | Test Ka-Band Components
|  |  |  | 05.05.04 | Transponder | 05.05.04.01 | Investigate Commercially Available Deep Space Transponders
[6 empty] | 05.05.04.02 | Procure Selected Transponders
[6 empty] | 05.05.04.03 | Test Transponders
|  |  |  | 05.05.05 | High Gain Antenna (HGA) | 05.05.05.01 | Investigate Commercially Available HGAs
[6 empty] | 05.05.05.02 | Design HGA Type
[6 empty] | 05.05.05.03 | Procure Selected HGA
[6 empty] | 05.05.05.04 | Test HGAs
|  |  |  | 05.05.06 | Medium Gain Antenna (MGA) | 05.05.06.01 | Investigate Commercially Available MGAs
[6 empty] | 05.05.06.02 | Design MGA Type
[6 empty] | 05.05.06.03 | Procure Selected MGA
[6 empty] | 05.05.06.04 | Test MGAs
|  |  |  | 05.05.07 | Low Gain Antenna (LGA) | 05.05.07.01 | Investigate Commercially Available LGAs
[6 empty] | 05.05.07.02 | Design LGA Type
[6 empty] | 05.05.07.03 | Procure Selected LGA
[6 empty] | 05.05.07.04 | Test LGAs
|  |  |  | 05.05.08 | Switches | 05.05.08.01 | Investigate Commercially Available Switches
[6 empty] | 05.05.08.02 | Design Switches Type
[6 empty] | 05.05.08.03 | Procure Selected Switches
[6 empty] | 05.05.08.04 | Test Switches
|  |  |  | 05.05.09 | Communication System Functional Testing | 05.05.09.01 | Develop Test Procedures
[6 empty] | 05.05.09.02 | Prepare Support Bus for Test
[6 empty] | 05.05.09.03 | Perform Communication System Functional Test to Qualification Standards
[6 empty] | 05.05.09.04 | Produce Testing Report
|  |  |  | 05.05.10 | Communication System Environmental Testing | 05.05.10.01 | Develop Test Procedures
[6 empty] | 05.05.10.02 | Prepare Support Bus for Test
[6 empty] | 05.05.10.03 | Perform Communication System Environmental Test to Qualification Standards
[6 empty] | 05.05.10.04 | Produce Testing Report
|  |  | Thermal Subsystem 05.06 | 05.06.01 | Thermal Management | 05.06.01.01 | Manage Thermal Team Members
[6 empty] | 05.06.01.02 | Interface between other subsystems
[6 empty] | 05.06.01.03 | Communicate with Flight System Management
|  |  |  | 05.06.02 | Heaters | 05.06.02.01 | Investigate Commercially Available Heaters
[6 empty] | 05.06.02.02 | Determine Heater Sizing
[6 empty] | 05.06.02.03 | Procure Selected Heaters
[6 empty] | 05.06.02.04 | Test Heaters
|  |  |  | 05.06.03 | Radiators | 05.06.03.01 | Investigate Commercially Available Temperature Control Devices
[6 empty] | 05.06.03.02 | Determine Radiator Sizing
[6 empty] | 05.06.03.03 | Procure Selected Radiators
[6 empty] | 05.06.03.04 | Test Radiators
|  |  |  | 05.06.04 | Thermal Monitoring System | 05.06.04.01 | Investigate Commercially Available Temperature Sensors
[6 empty] | 05.06.04.02 | Procure Selected Devices for System
[6 empty] | 05.06.04.03 | Test Thermal Monitoring System
|  |  |  | 05.06.05 | Thermal System Functional Testing | 05.06.04.01 | Develop Test Procedures
[6 empty] | 05.06.04.02 | Prepare Support Bus for Test
[6 empty] | 05.06.04.03 | Perform Thermal System Functional Test to Qualification Standards
[6 empty] | 05.06.04.04 | Produce Testing Report
|  |  |  | 05.06.06 | Thermal System Environmental Testing | 05.06.05.01 | Develop Test Procedures
[6 empty] | 05.06.05.02 | Prepare Support Bus for Test
[6 empty] | 05.06.05.03 | Perform Thermal System Environmental Test to Qualification Standards
[6 empty] | 05.06.05.04 | Produce Testing Report
|  |  | Guidance, Navigation and Control (GNC) Subsystem 05.07 | 05.07.01 | GNC Management | 05.07.01.01 | Manage GNC Team Members
[6 empty] | 05.07.01.02 | Interface between other subsystems
[6 empty] | 05.07.01.03 | Communicate with the Flight System Management
|  |  |  | 05.07.02 | APIC OpNav Camera | 05.07.02.01 | Investigate Commercially Available APIC Camera
[6 empty] | 05.07.02.02 | Procure Selected APIC Camera
[6 empty] | 05.07.02.03 | Test APIC Camera
|  |  |  | 05.07.03 | GNC System Functional Testing | 05.07.03.01 | Develop Test Procedures
[6 empty] | 05.07.03.02 | Prepare Support Bus for Test
[6 empty] | 05.07.03.03 | Perform GNC System Functional Test to Qualification Standards
[6 empty] | 05.07.03.04 | Produce Testing Report
|  |  |  | 05.07.04 | GNC System Environmental Testing | 05.07.04.01 | Develop Test Procedures
[6 empty] | 05.07.04.02 | Prepare Support Bus for Test
[6 empty] | 05.07.04.03 | Perform GNC System Environmental Test to Qualification Standards
[6 empty] | 05.07.04.04 | Produce Testing Report
|  |  | ADCS Subsystem 05.08 | 05.08.01 | ADCS Management | 05.08.01.01 | Manage ADCS Team Members
[6 empty] | 05.08.01.02 | Interface between other subsystems
[6 empty] | 05.08.01.03 | Communication with Flight System Management
|  |  |  | 05.08.02 | Sun Sensors | 05.08.02.01 | Investigate Commercially Available Sun Sensors
[6 empty] | 05.08.02.02 | Procure Selected Sun Sensors
[6 empty] | 05.08.02.03 | Test Sun Sensors
|  |  |  | 05.08.03 | Inertial Measurement Units (IMUs) | 05.08.03.01 | Investigate Commercially Available IMUs
[6 empty] | 05.08.03.02 | Procure Selected IMUs
[6 empty] | 05.08.03.03 | Test IMUs
|  |  |  | 05.08.04 | Star Trackers | 05.08.04.01 | Investigate Commercially Available Star Trackers
[6 empty] | 05.08.04.02 | Procure Selected Star Trackers
[6 empty] | 05.08.04.03 | Test Star Trackers
|  |  |  | 05.08.05 | Control Moment Gyroscope (CMGs) | 05.08.05.01 | Investigate Commercially Available CMGs
[6 empty] | 05.08.05.02 | Research CMGs design, sizing, and layout
[6 empty] | 05.08.05.03 | Procure Selected CMGs
[6 empty] | 05.08.05.04 | Test CMGs
|  |  |  | 05.08.06 | ADCS System Functional Testing | 05.08.06.01 | Develop Test Procedures
[6 empty] | 05.08.06.02 | Prepare Support Bus for Test
[6 empty] | 05.08.06.03 | Perform ADCS System Functional Test to Qualification Standards
[6 empty] | 05.08.06.04 | Produce Testing Report
|  |  |  | 05.08.07 | ADCS System Environmental Testing | 05.08.07.01 | Develop Test Procedures
[6 empty] | 05.08.07.02 | Prepare Support Bus for Test
[6 empty] | 05.08.07.03 | Perform ADCS System Environmental Test to Qualification Standards
[6 empty] | 05.08.07.04 | Produce Testing Report
|  |  | Structures and Mechanisms 05.09 | 05.09.01 | Bus Structure | 05.09.01.01 | Bus Structure Management | 05.09.01.01.01 | Manage Structure Team Members
[8 empty] | 05.09.01.01.02 | Interface between other subsystems
[8 empty] | 05.09.01.01.03 | Communication with Flight System Management
[6 empty] | 05.09.01.02 | Bus Structure Development | 05.09.01.02.01 | Shielding | 05.09.01.02.01.01 | Research Optimal Shielding Properties
[10 empty] | 05.09.01.02.01.02 | Design Compatible Shielding
[10 empty] | 05.09.01.02.01.03 | Run FEA on Shielding
[10 empty] | 05.09.01.02.01.04 | Run Thermal Test on Shielding
[10 empty] | 05.09.01.02.01.05 | Manufacture Shielding
[10 empty] | 05.09.01.02.01.06 | Test Shielding
[8 empty] | 05.09.01.02.02 | Mechanisms | 05.09.01.02.02.01 | Research interfaces between instrumentation and structure
[10 empty] | 05.09.01.02.02.02 | Develop modeling and CAD drawings
[10 empty] | 05.09.01.02.02.03 | Run FEA on mechanism loading
[10 empty] | 05.09.01.02.02.04 | Manufacture mechanism processes
[10 empty] | 05.09.01.02.02.05 | Test instrumentation mechanisms
[8 empty] | 05.09.01.02.03 | Primary Structure and Interfaces | 05.09.01.02.03.01 | Research materials
[10 empty] | 05.09.01.02.03.02 | Develop modeling and CAD drawings
[10 empty] | 05.09.01.02.03.03 | Run FEA on primary structure and interfaces
[10 empty] | 05.09.01.02.03.04 | Manufacture primary structure
[10 empty] | 05.09.01.02.03.05 | Conduct testing processes on primary structure
|  |  |  | 05.09.02 | Instrument Housing Module (IHM) Structure | 05.09.02.01 | IHM Structure Management | 05.09.02.01.01 | Manage IHM Structure Team members
[8 empty] | 05.09.02.01.02 | Interface between other subsystems
[8 empty] | 05.09.02.01.03 | Communicate with Flight System Management
[6 empty] | 05.09.02.02 | IHM Structure Development | 05.09.02.02.01 | Shielding | 05.09.02.02.01.01 | Research Optimal Shielding Properties
[10 empty] | 05.09.02.02.01.02 | Design Compatible Shielding
[10 empty] | 05.09.02.02.01.03 | Run FEA on Shielding
[10 empty] | 05.09.02.02.01.04 | Run Thermal Test on Shielding
[10 empty] | 05.09.02.02.01.05 | Manufacture Shielding
[10 empty] | 05.09.02.02.01.06 | Test Shielding
[8 empty] | 05.09.02.02.02 | Mechanisms | 05.09.02.02.02.01 | Research interfaces between instrumentation and structure
[10 empty] | 05.09.02.02.02.02 | Develop modeling and CAD drawings
[10 empty] | 05.09.02.02.02.03 | Run FEA on mechanism loading
[10 empty] | 05.09.02.02.02.04 | Manufacture mechanism processes
[10 empty] | 05.09.02.02.02.05 | Test instrumentation mechanisms
[8 empty] | 05.09.02.02.03 | Primary Structure and Interfaces | 05.09.02.02.03.01 | Research materials
[10 empty] | 05.09.02.02.03.02 | Develop modeling and CAD drawings
[10 empty] | 05.09.02.02.03.03 | Run FEA on primary structure and interfaces
[10 empty] | 05.09.02.02.03.04 | Manufacture primary structure
[10 empty] | 05.09.02.02.03.05 | Conduct testing processes on primary structure
[8 empty] | 05.09.02.02.04 | IHM Functional Testing | 05.09.02.02.04.01 | Develop Test Procedures
[10 empty] | 05.09.02.02.04.02 | Prepare IHM for Test
[10 empty] | 05.09.02.02.04.03 | Perform IHM Functional Test to Qualification Standards
[10 empty] | 05.09.02.02.04.04 | Produce Testing Report
[8 empty] | 05.09.02.02.05 | IHM Environmental Testing | 05.09.02.02.05.01 | Develop Test Procedures
[10 empty] | 05.09.02.02.05.02 | Prepare IHM for Test
[10 empty] | 05.09.02.02.05.03 | Perform IHM Environmental Test to Qualification Standards
|  |  |  | 05.09.03 | Solar Array Drive Assembly | 05.09.03.01 | Investigate Commercially Available Solar Array Drive Assemblies
[6 empty] | 05.09.03.02 | Procure Selected Solar Array Drive Assemblies
[6 empty] | 05.09.03.03 | Procure Structure around Solar Array Provided by Deployable Space Systems
[6 empty] | 05.09.03.04 | Test Solar Array Drive Assemblies
[6 empty] | 05.09.03.05 | Integrate to Bus Structure
|  |  |  | 05.09.04 | Thruster Gimbal/Actuator | 05.09.04.01 | Investigate Commercially Available Thruster Gimbals
[6 empty] | 05.09.04.02 | Procure Selected Thruster Gimbals
[6 empty] | 05.09.04.03 | Test Thruster Gimbals
[6 empty] | 05.09.04.04 | Integrate to Bus Structure
|  |  |  | 05.09.05 | ROSA Release Mechanisms | 05.09.05.01 | Investigate Commercially Available Release Mechanisms
[6 empty] | 05.09.05.02 | Procure Selected Release Mechanisms
[6 empty] | 05.09.05.03 | Test ROSA Release Mechanisms
[6 empty] | 05.09.05.04 | Integrate to Bus Structure
|  |  |  | 05.09.06 | Pre-loaded ROSA Hinges | 05.09.06.01 | Investigate Commercially Available Pre-loaded hinges
[6 empty] | 05.09.06.02 | Procure Selected Pre-loaded hinges
[6 empty] | 05.09.06.03 | Test Pre-loaded ROSA hinges
[6 empty] | 05.09.06.04 | Integrate to Bus Structure
|  |  |  | 05.09.07 | Synthetic Aperture Radar (SAR) Release Mechanism | 05.09.07.01 | Investigate Commercially Available release mechanisms
[6 empty] | 05.09.07.02 | Procure Selected release mechanisms
[6 empty] | 05.09.07.03 | Test SAR release mechanisms
[6 empty] | 05.09.07.04 | Integrate to Bus Structure
|  |  |  | 05.09.08 | Pre-loaded Synthetic Aperture Radar (SAR) Hinges | 05.09.08.01 | Investigate Commercially Available Pre-loaded hinges
[6 empty] | 05.09.08.02 | Procure Selected Pre-loaded hinges
[6 empty] | 05.09.08.03 | Test Pre-loaded SAR hinges
[6 empty] | 05.09.06.04 | Integrate to Bus Structure
|  |  |  | 05.09.09 | Imager Lens Cap Mechanism | 05.09.09.01 | Investigate Commercially Available lens cap mechanisms
[6 empty] | 05.09.09.02 | Procure Selected lens cap mechanisms
[6 empty] | 05.09.09.03 | Test lens cap mechanisms
[6 empty] | 05.09.06.04 | Integrate to Bus Structure
|  |  |  | 05.09.10 | Structural Environmental Testing | 05.09.10.01 | Develop Test Procedures
[6 empty] | 05.09.10.02 | Prepare Bus and IHM for Test
[6 empty] | 05.09.10.03 | Perform Structure System Environmental Test to Qualification Standards
[6 empty] | 05.09.10.04 | Produce Testing Report
|  |  | C&DH Subsystem 05.10 | 05.10.01 | C&DH Management | 05.10.01.01 | Manage C&DH Team Members
[6 empty] | 05.10.01.02 | Interface between other subsystems
[6 empty] | 05.10.01.03 | Communication with Flight System Management
|  |  |  | 05.10.02 | Flight Processors | 05.10.02.01 | Investigate Commercially Available Flight Processors
[6 empty] | 05.10.02.02 | Procure Selected Flight Processors
[6 empty] | 05.10.02.03 | Test Flight Processors
|  |  |  | 05.10.03 | Interface Cards | 05.10.03.01 | Investigate Commercially Available Interface Cards
[6 empty] | 05.10.03.02 | Procure Selected Interface Cards
[6 empty] | 05.10.03.03 | Test Interface Cards
|  |  |  | 05.10.04 | Data Storage | 05.10.04.01 | Investigate Commercially Available Data Storage
[6 empty] | 05.10.04.02 | Procure Selected Data Storage
[6 empty] | 05.10.04.03 | Test Data Storage
|  |  |  | 05.10.05 | Comms Cards | 05.10.05.01 | Investigate Commercially Available Comms Cards
[6 empty] | 05.10.05.02 | Procure Selected Comms Cards
[6 empty] | 05.10.05.03 | Test Comms Cards
|  |  |  | 05.10.06 | Arbiter | 05.10.06.01 | Investigate Commercially Available RS-485 Arbiter
[6 empty] | 05.10.06.02 | Procure RS-485 Arbiter
[6 empty] | 05.10.06.03 | Test RS-485 Arbiter
|  |  |  | 05.10.07 | Power Card | 05.10.07.01 | Investigate Commercially Available Power Card
[6 empty] | 05.10.07.02 | Design Power Card
[6 empty] | 05.10.07.03 | Test Power Card
|  |  |  | 05.10.08 | C&DH System Functional Testing | 05.10.08.01 | Develop Test Procedures
[6 empty] | 05.10.08.02 | Prepare Support Bus for Test
[6 empty] | 05.10.08.03 | Perform C&DH System Functional Test to Qualification Standards
[6 empty] | 05.10.08.04 | Produce Testing Report
|  |  |  | 05.10.09 | C&DH System Environmental Testing | 05.10.09.01 | Develop Test Procedures
[6 empty] | 05.10.09.02 | Prepare Support Bus for Test
[6 empty] | 05.10.09.03 | Perform C&DH System Environmental Test to Qualification Standards
[6 empty] | 05.10.09.04 | Produce Testing Report
|  |  |  | 05.10.10 | Bus Integration and Testing | 05.10.10.01 | Bus Integration | 05.10.10.01.01 | Integrate Subsystems into Bus
[6 empty] | 05.10.10.02 | Bus Functional Testing | 05.10.10.02.01 | EPS Qualification Test | 05.10.10.02.01.01 | Develop Test Procedures
[10 empty] | 05.10.10.02.01.02 | Prepare Bus for Test
[10 empty] | 05.10.10.02.01.03 | Perform Bus EPS Test to Qualification Standards
[10 empty] | 05.10.10.02.01.04 | Produce Testing Report
[8 empty] | 05.10.10.02.02 | RF System Qualification Test | 05.10.10.02.02.01 | Develop Test Procedures
[10 empty] | 05.10.10.02.02.02 | Prepare Bus for Test
[10 empty] | 05.10.10.02.02.03 | Perform Bus RF System Test to Qualification Standards
[10 empty] | 05.10.10.02.02.04 | Produce Testing Report
[8 empty] | 05.10.10.02.03 | Communications Qualification Test | 05.10.10.02.03.01 | Develop Test Procedures
[10 empty] | 05.10.10.02.03.02 | Prepare Bus for Test
[10 empty] | 05.10.10.02.03.03 | Perform Support Bus Communication Test to Qualification Standards
[10 empty] | 05.10.10.02.03.04 | Produce Testing Report
[8 empty] | 05.10.10.02.04 | Sensors and Interface Qualification Test | 05.10.10.02.04.01 | Develop Test Procedures
[10 empty] | 05.10.10.02.04.02 | Prepare Bus for Test
[10 empty] | 05.10.10.02.04.03 | Perform Support Bus Sensor and Interface Test to Qualification Standards
[10 empty] | 05.10.10.02.04.04 | Produce Testing Report
[6 empty] | 05.10.10.03 | Bus Environmental Testing | 05.10.10.03.01 | Develop Test Procedures
[8 empty] | 05.10.10.03.02 | Prepare Support Bus for Test
[8 empty] | 05.10.10.03.03 | Perform Support Bus Environmental Tests to Qualification Standards
[8 empty] | 05.10.10.03.04 | Produce Testing Report
|  |  | Flight System Storage 05.12 | 05.12.01 | Clean Room Management | 05.12.01.01 | Manage Stock and Order of Clean Room
|  |  |  | 05.12.02 | Environment Control | 05.12.02.01 | Maintain Safe Environment for Flight System Storage
|  |  |  | 05.12.03 | Security Services | 05.12.03.01 | Provide Security for Flight System Storage Facility
|  |  | Payload 05.13 | 05.13.01 | Payload Management | 05.13.01.01 | Manage Payload Team Members
[6 empty] | 05.13.01.02 | Interface between Spacecraft Bus and IHM
|  |  |  | 05.13.02 | Cassegrain telescope | 05.13.02.01 | Research Cassegrain Telescope Properties
[6 empty] | 05.13.02.02 | Design Compatible Cassegrain Telescope
[6 empty] | 05.13.02.03 | Manufacture Cassegrain Telescope
[6 empty] | 05.13.02.04 | Test Cassegrain Telescope Function
|  |  |  | 05.13.03 | Visible CCD Board | 05.13.03.01 | Investigate Commercially Available Visible CCD Boards
[6 empty] | 05.13.03.02 | Procure Selected Visible CCD Board
[6 empty] | 05.13.03.03 | Test Visible CCD Board
|  |  |  | 05.13.04 | Infrared CCD Board | 05.13.04.01 | Investigate Commercially Available Infrared CCD Boards
[6 empty] | 05.13.04.02 | Procure Selected Infrared CCD Board
[6 empty] | 05.13.04.03 | Test Infrared CCD Board
|  |  |  | 05.13.05 | Pickoff Mirror | 05.13.05.01 | Investigate Previous Pickoff Mirror Designs
[6 empty] | 05.13.05.02 | Design Pickoff Mirror Compatable to Imager
[6 empty] | 05.13.05.03 | Test Pickoff Mirror Function
|  |  |  | 05.13.06 | Synthetic Apaerture Radar (SAR) Antenna | 05.13.06.01 | Design Internal Electronics
[6 empty] | 05.13.06.02 | Manufacture SAR System
[6 empty] | 05.13.06.03 | Test SAR Surface Dielectric Detection Capabilities
|  |  |  | 05.13.07 | Imager Lens Cap | 05.13.07.01 | Investigate Commercially Available lens caps
[6 empty] | 05.13.07.02 | Develop CAD modelling
[6 empty] | 05.13.07.03 | Procure Selected lens cap
[6 empty] | 05.13.07.04 | Test imager lens cap
|  |  |  | 05.13.08 | Payload Integration to IHM | 05.13.08.01 | Integrate Payload Instrumentation to IHM Structure
[6 empty] | 05.13.08.02 | Payload Instrument Functional Testing | 05.13.08.02.01 | Develop Test Procedures
[8 empty] | 05.13.08.02.02 | Prepare Payload for Test
[8 empty] | 05.13.08.02.03 | Perform Payload Functional Test to Qualification Standards
[8 empty] | 05.13.08.02.04 | Produce Testing Report
[6 empty] | 05.13.08.03 | Payload Instrument Environmental Testing | 05.13.08.03.01 | Develop Test Procedures
[8 empty] | 05.13.08.03.02 | Prepare Payload for Test
[8 empty] | 05.13.08.03.03 | Perform Payload Environmental Tests to Qualification Standards
[8 empty] | 05.13.08.03.04 | Produce Testing Report
|  |  |  | 05.13.09 | Payload Attachment Fitting (PAF) | 05.13.09.01 | Research PAF capabilities and bus integration
[6 empty] | 05.13.09.02 | Perform Test Fitting to SC
[6 empty] | 05.13.09.03 | Procure or design PAF for configuration
|  | Mission Operation 06 | Mission Operation Management 06.01 | 06.01.01 | Manage the Mission Operation Teams
|  |  | Phase 1-3 Operations 06.02 | 06.02.01 | Mission Planning | 06.02.01.01 | Execute trajectory, engineering, and science plans to enter pre-positioned orbit and perform science observations
[6 empty] | 06.02.01.02 | Allocate and manage mission consumables, ensuring sufficient amounts remain for primary mission
|  |  |  | 06.02.02 | Mission Operations | 06.02.02.01 | Monitor and trend spacecraft performance and health as data is downlinked
[6 empty] | 06.02.02.02 | Upload Command Sequences for the spacecraft to execute autonomous science observations and health checks
[6 empty] | 06.02.02.03 | Configure and Control Ground Data Systems
|  |  |  | 06.02.03 | Navigation and Orbit Operations | 06.02.03.01 | Design Trajectories and monitor current spacecraft trajectory
[6 empty] | 06.02.03.02 | Determine Position and Velocity
[6 empty] | 06.02.03.03 | Design Maneuvers and Gravity Assists to reach Pre-Positioned Orbit
|  |  |  | 06.02.04 | Spacecraft Operations | 06.02.04.01 | Ensure spacecraft safety and health
[6 empty] | 06.02.04.02 | Analyze and Address Anomalies
[6 empty] | 06.02.04.03 | Maintain flight software
|  |  |  | 06.02.05 | Payload Operations | 06.02.05.01 | Ensure payload safety and health
[6 empty] | 06.02.05.02 | Analyze and Address Anomalies
|  |  |  | 06.02.06 | Science Operations | 06.02.06.01 | Create science plans to be uplinked to the spacecraft
[6 empty] | 06.02.06.02 | Analyze downlinked science data to ensure requirements are met
|  |  | Phase 4-6 Operations 06.03 | 06.03.01 | Mission Planning | 06.03.01.01 | Execute trajectory, engineering, and science plans to exit pre-positioned orbit and enter transfer trajectory
[6 empty] | 06.03.01.02 | Allocate and manage mission consumables, ensuring sufficient amounts remain for ISO encounter
|  |  |  | 06.03.02 | Mission Operations | 06.03.02.01 | Monitor and trend spacecraft performance and health as data is downlinked
[6 empty] | 06.03.02.02 | Upload Command Sequences for the spacecraft to execute autonomous science observations and health checks
[6 empty] | 06.03.02.03 | Configure and Control Ground Data Systems
|  |  |  | 06.03.03 | Navigation and Orbit Operations | 06.03.03.01 | Design Trajectories and monitor current spacecraft trajectory
[6 empty] | 06.03.03.02 | Determine Position and Velocity
[6 empty] | 06.03.03.03 | Design Maneuvers and Gravity Assists to reach Pre-Positioned Orbit
|  |  |  | 06.03.04 | Spacecraft Operations | 06.03.04.01 | Ensure spacecraft safety and health
[6 empty] | 06.03.04.02 | Analyze and Address Anomalies
[6 empty] | 06.03.04.03 | Maintain flight software
|  |  |  | 06.03.05 | Payload Operations | 06.03.05.01 | Ensure payload safety and health
[6 empty] | 06.03.05.02 | Analyze and Address Anomalies
|  |  |  | 06.03.06 | Science Operations | 06.03.06.01 | Create science plans to be uplinked to the spacecraft
[6 empty] | 06.03.06.02 | Analyze downlinked science data to ensure requirements are met
|  |  | Data Services 06.04 | 06.04.01 | Receive, Stage, Transport, Process, Display, and Archive Data
|  |  |  | 06.04.02 | Transmit Commands
|  |  |  | 06.04.03 | Manage Computer, communications and database
|  |  | Computer and Communication Support 06.05 | 06.05.01 | Maintain Hardware
|  |  |  | 06.05.02 | Maintain Data Links
|  |  | Software Development and Maintenance 06.06 | 06.06.01 | Maintain the Software System
|  |  |  | 06.06.02 | Upgrade the Software System
|  |  |  | 06.06.03 | Train and certify operators
|  | Ground System 07 | Ground System Management 07.01 | 07.01.01 | Creation and implementation of communications, software and hardware integration and utilization
|  |  | Ground Systems Engineering 07.02 | 07.02.01 | Track requirements and architecture of the ground system
|  |  | DSN - Contractor 07.03 | 07.03.01 | Contact Scheduling
|  |  |  | 07.03.02 | Interface with Ground System
|  |  | Mission Operation Management 07.04 | 07.04.01 | Manage the mission operation center by communicating with the science operations, mission control, and data storage and network management. Update customer on the status of the overall mission
|  |  | Science Operations Center 07.05 | 07.05.01 | Manage the science operations center. Communicate with mission operation management on the state of the science being conducted.
|  |  |  | 07.05.02 | Determine Spacecraft/Payload Operations to Achieve Science Return
|  |  |  | 07.05.03 | Inform Mission Control Center of necessary SC Operations
|  |  |  | 07.05.04 | Generate Shape Model of ISO (collection of 3D points on the surface of the ISO)
|  |  |  | 07.05.05 | Determine Rotation Rate of ISO (from light curves generated from OpNav images)
|  |  |  | 07.05.06 | Determine Spin Axis direction in inertial space
|  |  |  | 07.05.07 | Determine Mean Dimension of the ISO
|  |  |  | 07.05.08 | Produce generated visual images of the illuminated ISO surface
|  |  |  | 07.05.09 | Produce Generated infrared images of the ISO surface
|  |  |  | 07.05.10 | Distribute Science Products to End Users (Customer or Science Community)
|  |  | Mission Control Center 07.06 | 07.06.01 | Manage the mission control center. Communicate with mission operation management on the state of the mission
|  |  |  | 07.06.02 | Send Commands of the Spacecraft and Payload through DSN
|  |  |  | 07.06.03 | Monitor spacecraft performance
|  |  |  | 07.06.04 | Update ISO ephemeris
Update Earth ephemeris
Update s/c ephemeris
|  |  |  | 07.06.05 | Request and Receive Data to/from DSN as necessary
|  |  | Data Storage and Network 07.07 | 07.07.01 | Data Storage and Network Management
|  |  |  | 07.07.02 | Condition Mission Data for Science Storage
|  |  |  | 07.07.03 | Store Mission Data
|  |  |  | 07.07.04 | Connect Mission and Telemetry Commands to DSN Station Control Center
|  |  |  | 07.07.05 | Connect Mission Data and Science Products to End Users (Customer)
|  |  | Cyber Security 07.08 | 07.08.01 | Protect data from hacking or being shared illegally
|  |  | Backup Power 07.09 | 07.09.01 | Provide Backup Power for Project Operation Centers
|  | Launch Services 08 | Program Launch Services Manager 08.01 | 08.01.01 | COSMIC program Point of Contact to contractors
|  |  | Regulation Coordinators 08.02 | 08.02.01 | Range Safety | 08.02.01.01 | Coordinate with the Range Safety Supervisor to ensure open airways and safe fueling operations
|  |  |  | 08.02.02 | FAA | 08.02.02.01 | Coordinate with FAA to ensure the manufacturing and launch of the flight system follows FAA protocol
|  |  | Space X - Contractor 08.03 | 08.03.01 | Launch and Integration Services
|  |  | Fuel Contractor 08.04 | 08.04.01 | Fuel Production and Fuel Loading Services
|  | System Integration and Testing 09 | System Integration and Testing Management 09.01 | 09.01.01 | Develop Test Procedures
|  |  |  | 09.01.02 | Develop Integration Procedures
|  |  |  | 09.01.03 | Manage Nonconformities (NC)
|  |  |  | 09.01.04 | Create Timelines & Schedules
|  |  | System I&T Systems Engineering 09.02 | 09.02.01 | Develop Verification Requirements
|  |  |  | 09.02.02 | Integrate Test Plans and Procedures
|  |  |  | 09.02.03 | Verify I&T Requirements are Met
|  |  | Flight System Facilities 09.03 | 09.03.01 | Facilities and Utilities Management | 09.03.01.01 | Manage facilities in Use
[6 empty] | 09.03.01.02 | Manage Utilities
|  |  |  | 09.03.02 | Production | 09.03.02.01 | Manage Production Personnel
[6 empty] | 09.03.02.02 | Assemble Flight System Components with Production Facilities and Grounds
[6 empty] | 09.03.02.03 | Provide Production Equipment such as Cranes, Lifts, and other necessary equipment
|  |  |  | 09.03.03 | Maintenance | 09.03.03.01 | Manage Maintenance Equipment and Personnel
[6 empty] | 09.03.03.02 | Maintain Equipment
[6 empty] | 09.03.03.03 | Maintain Facility
|  |  |  | 09.03.04 | Facility Security | 09.03.04.01 | Supervise and protect facility and faculty
|  |  |  | 09.03.05 | Shipping | 09.03.05.01 | Pack Flight System for Shipping
[6 empty] | 09.03.05.02 | Manage third-party shipping operations to move spacecraft between facilities
[6 empty] | 09.03.05.03 | Unpack Flight System
|  |  | Flight System Functional Testing 09.04 | 09.04.01 | Functional Test | 09.04.01.01 | Procure Test Procedures
[6 empty] | 09.04.01.02 | Package Flight System for Shipping
[6 empty] | 09.04.01.03 | Ship Flight System to Testing Facility
[6 empty] | 09.04.01.04 | Prepare Flight System for Test
[6 empty] | 09.04.01.05 | Perform Functional Test on Flight System to Qualification Level Standards
[6 empty] | 09.04.01.06 | Produce testing report
|  |  |  | 09.04.02 | Full Functional Test | 09.04.02.01 | Procure Test Procedures
[6 empty] | 09.04.02.02 | Package Flight System for Shipping
[6 empty] | 09.04.02.03 | Ship Flight System to Testing Facility
[6 empty] | 09.04.02.04 | Prepare Flight System for Test
[6 empty] | 09.04.02.05 | Perform Functional Test on Flight System
[6 empty] | 09.04.02.06 | Produce testing report
|  |  |  | 09.04.03 | Solar Panel First Motion Deployment Test | 09.04.03.01 | Procure Test Procedures
[6 empty] | 09.04.03.02 | Prepare Flight System for Test
[6 empty] | 09.04.03.03 | Perform Functional Test
[6 empty] | 09.04.03.04 | Produce Testing Report
|  |  | Flight System Environmental Testing 09.05 | 09.05.01 | EMI/EMC Qualification Test | 09.05.01.01 | Procure Test Procedures
[6 empty] | 09.05.01.02 | Package Flight System for Shipping
[6 empty] | 09.05.01.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.01.04 | Prepare Flight System for Test
[6 empty] | 09.05.01.05 | Perform Test on Flight System to Qualification Level Standards
[6 empty] | 09.05.01.06 | Produce testing report
|  |  |  | 09.05.02 | Thermal Vacuum Qualification Test | 09.05.02.01 | Procure Test Procedures
[6 empty] | 09.05.02.02 | Package Flight System for Shipping
[6 empty] | 09.05.02.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.02.04 | Prepare Flight System in Vacuum Chamber for Test
[6 empty] | 09.05.02.05 | Perform Test on Flight System to Qualification Level Standards
[6 empty] | 09.05.02.06 | Produce testing report
|  |  |  | 09.05.03 | Acoustic Qualification Test | 09.05.03.01 | Procure Test Procedures
[6 empty] | 09.05.03.02 | Package Flight System for Shipping
[6 empty] | 09.05.03.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.03.04 | Prepare Flight System for Test
[6 empty] | 09.05.03.05 | Perform Test on Flight System to Qualification Level Standards
[6 empty] | 09.05.03.06 | Produce testing report
|  |  |  | 09.05.04 | Vibration Qualification Test | 09.05.04.01 | Procure Test Procedures
[6 empty] | 09.05.04.02 | Package Flight System for Shipping
[6 empty] | 09.05.04.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.04.04 | Prepare Flight System for Test
[6 empty] | 09.05.04.05 | Perform Test on Flight System to Qualification Level Standards
[6 empty] | 09.05.04.06 | Produce testing report
|  |  |  | 09.05.05 | EMI/EMC Flight Acceptance Test | 09.05.05.01 | Procure Test Procedures
[6 empty] | 09.05.05.02 | Package Flight System for Shipping
[6 empty] | 09.05.05.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.05.04 | Prepare Flight System for Test
[6 empty] | 09.05.05.05 | Perform Test on Flight System to Flight Acceptance
[6 empty] | 09.05.05.06 | Produce testing report
|  |  |  | 09.05.06 | Thermal Vacuum Flight Acceptance Test | 09.05.06.01 | Procure Test Procedures
[6 empty] | 09.05.06.02 | Package Flight System for Shipping
[6 empty] | 09.05.06.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.06.04 | Prepare Flight System in Vacuum Chamber for Test
[6 empty] | 09.05.06.05 | Perform Test on Flight System to Flight Acceptance Level Standards
[6 empty] | 09.05.06.06 | Produce testing report
|  |  |  | 09.05.07 | Acoustic Flight Acceptance Test | 09.05.07.01 | Procure Test Procedures
[6 empty] | 09.05.07.02 | Package Flight System for Shipping
[6 empty] | 09.05.07.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.07.04 | Prepare Flight System for Test
[6 empty] | 09.05.07.05 | Perform Test on Flight System to Flight Acceptance Level Standards
[6 empty] | 09.05.07.06 | Produce testing report
|  |  |  | 09.05.08 | Vibration Flight Acceptance Test | 09.05.08.01 | Procure Test Procedures
[6 empty] | 09.05.08.02 | Package Flight System for Shipping
[6 empty] | 09.05.08.03 | Ship Flight System to Testing Facility
[6 empty] | 09.05.08.04 | Prepare Flight System for Test
[6 empty] | 09.05.08.05 | Perform Test on Flight System to Flight Acceptance Level Standards
[6 empty] | 09.05.08.06 | Produce testing report
|  |  | Flight System Mass Properties Evaluation 09.06 | 09.06.01 | Procure Test Procedures
|  |  |  | 09.06.02 | Package Flight System for Shipping
|  |  |  | 09.06.03 | Ship Flight System to Testing Facility
|  |  |  | 09.06.04 | Prepare Flight System for Test
|  |  |  | 09.06.05 | Perform Mass Properties Evaluation Test
|  |  |  | 09.06.08 | Produce testing report and determine Mass Properties
|  |  | Flight-Ground Systems Link Test 09.07 | 09.07.01 | Uplink and Downlink Flight System to the Ground Station Terminal to ensure connection
|  |  | Ground Support Equipment (GSE) 09.08 | 09.08.01 | Design GSE
|  |  |  | 09.08.02 | Manufacture GSE
|  |  |  | 09.08.03 | Verify GSE to expected performance
|  |  | Flight System Integration 09.09 | 09.09.01 | IHM Integration
|  |  |  | 09.09.02 | Bus Integration
|  |  |  | 09.09.03 | Integrate Solar Panels
|  |  |  | 09.09.04 | Integrate Antennas
|  |  |  | 09.09.05 | Integrate Radiators
|  |  |  | 09.09.06 | Finalization
|  |  | Launch System Integration 09.10 | 09.10.01 | Third-Party Chem Propellant Loading
|  |  |  | 09.10.02 | Unpack Flight System and GSE at PPF
|  |  |  | 09.10.03 | Deliver Flight System and GSE to Payload Processing Facility (PPF)
|  |  |  | 09.10.04 | Integrate with Fairing
|  |  |  | 09.10.05 | SpaceX Activities